## Blank
Event Cheat Sheet
Event Information
Name of Event:
Date of Event:
Time of Event:
Location of Event:
Lead of Event:
Groups/Orgs to Target:
NOTES:
Marketing Timeline
Tasks | Deadline | Person Responsible | Notes
PHASE 1 (2 months)
Submit CF Student & Employer Flyer to Branding for Approval
Confirm Event on UH Main Events Calendar
Confirm Event on UCS Events Calendar
Confirm Event in Cougar Pathway
Send CP Employer Message 1
Send Student Message 1
SM 1 Post
Post on Campus Wide Digital Signage
PHASE 2 (1 month)
Send CP Employer Message 2
Send Student Message 2 (1 month away)
Distribute Flyers Campus Wide
SM Post 2 (1 Month Away)
Submit to CoogNews
Send emails to target groups
PHASE 3 ( 3 weeks)
Submit to CoogNews
SM Post 3
PHASE 4 (2 weeks)
Submit to CoogNews
Send CP Employer Message 4
Send Student Message 4
SM Post 4
PHASE 5 (1 week)
Submit to CoogNews (Monday of week before event; to post on Thursday)
Send CP Employer Message 5
Send Student Message 5
Send emails to target groups
SM Post 5
PHASE 6 (Day before event)
Send Student Message 5
SM Post 6

## Example
Event Cheat Sheet
Event Information
Name of Event: | Cougar Career Fair
Date of Event: | 2020-03-08
Time of Event: | 3-5pm
Location of Event: | Student Center
Lead of Event: | Shasta Cougar
Groups/Orgs to Target: | Transfer students
NOTES:
Areas of Responsibility
Volunteers
Tasks | Deadline | Person Responsible | Notes
Coordinate volunteer sign up and send messages to student organizations | 1 month prior to event
Follow up with volunteers 1 week prior to the event to confirm their attendance and give instructions | 1 week prior to event
Assign *student workers* day of event tasks & email | 1 week prior to event
Send our "Career Fair Field Trip" CP Message | 1 week prior to event
Assign student volunteer tasks & share with team | staff mtg before event |  | See "Volunteer Tasks" sheet
Meet volunteers at UCS and carry items | day of event
Communicate tasks to student volunteers | day of event
Coordinate volunteer sign out and sign in process | day of event
Coordinate sign in process for "CF- Field Trip" | day of event
Facilitate "Career Fair Field Trip" (top of hour) | day of event |  | 1PM, 2PM, 3PM
EDR TEAM RESPONSIBILITIES
Tasks | Deadline | Person Responsible | Notes
Create Career Fair in Cougar Pathway | beginning of each semester
Respond to employer questions and concerns | as needed
Follow up with employers one week prior to event | 1 week prior to event |  | confirm attendance & names
Monitor employer registration and report #s | each staff meeting
Pack items into crates according to lists | night before event
Coordinate employer check in table | day of event
STUDENT REGISTRATION
Tasks | Deadline | Person Responsible | Notes
Submit IT request for laptops, if needed | 1 week prior to event
Submit IT request for IT support | 1 week prior to event
Create Career Fair Kiosk in CP | 1 week prior to event
Set up excel spreadsheets for UH system & alumni | 1 week prior to event |  | saved in SharePoint
Report final attendance numbers | staff mtg after event
Unload and set up Kiosks and Dymo Printers | day of event
EVALUATIONS
Tasks | Deadline | Person Responsible | Notes
Create survey in Baseline | 1 week prior to event
Charge itouches & ipads | 1-2 days before event
Gather all evaluation materials and bring to event | day of event
Give instructions to volunteers | day of event
Confirm evaluations are being collected in system | day of event
Report final evaluation stats for both students and employers | staff mtg after event
MARKETING