## UGLS1063_Section_2
Project | Descr | Current Budget | YTD/PTD Rev/Exp | Open Cmt | Soft Cmt | BBA | PM
P779212 | FY07 CRDM Contingency | 232667.36 | 198453.67 | 0 | 0 | 34213.69
P779215 | FY07 CRDM Power Generator | 1069182.52 | 1069182.52 | 0 | 0 | 0
P779216 | FY07 CRDM Energy conservation | 160786.01 | 160786.01 | 0 | 0 | 0
P779217 | FY07 CRDM Classroom & Corridor | 166720.66 | 166720.66 | 0 | 0 | 0
P779218 | FY07 CRDM Cullen Closure | 85765.19 | 85765.19 | 0 | 0 | 0
P779219 | FY07 CRDM Security Cameras | 81142.45 | 81142.45 | 0 | 0 | 0
P779220 | FY07 CRDM Landscape/Framework | 192685 | 192685 | 0 | 0 | 0
P779222 | FY07 CRDM Code Blue Phones | 78545.92 | 78545.92 | 0 | 0 | 0
P779223 | FY07 CRDM Security Lighting | 57810 | 57810 | 0 | 0 | 0
P779224 | FY07 CRDM ADA Modifications | 74482.57 | 74482.57 | 0 | 0 | 0
P779226 | FY07 CRDM Enviro Remediation | 69223.66 | 69223.66 | 0 | 0 | 0
P779227 | FY07 CRDM Facilities Maint | 358040.06 | 358040.06 | 0 | 0 | 0
P779228 | FY07 CRDM Site infrastructure | 127384 | 127384 | 0 | 0 | 0
P779229 | FY07 CRDM Tunnel repairs | 15.24 | 15.24 | 0 | 0 | 0
P779230 | FY07 CRDM Cullen Perform Hall | 6825.44 | 6825.44 | 0 | 0 | 0
P779231 | FY07 CRDM Moores study | 16952 | 16952 | 0 | 0 | 0
P779232 | FY07 CRDM SSC1 Roof | 201609.06 | 201609.06 | 0 | 0 | 0
P779233 | FY07 CRDM Heyne waterproofing | 8654.75 | 8654.75 | 0 | 0 | 0
P779234 | FY07 CRDM Campus roof work | 204624.81 | 204624.81 | 0 | 0 | 0
P779235 | FY07 CRDM S&R-2 water remed | 61893.59 | 61893.59 | 0 | 0 | 0
P779236 | FY07 CRDM Fleming waterproof | 596881.27 | 596881.27 | 0 | 0 | 0
P779237 | FY07 CRDM GSB Chillers | 142804 | 142804 | 0 | 0 | 0
P779238 | FY07 CRDM Farish Hall roof | 47903 | 47903 | 0 | 0 | 0
P779244 | FY07 CRDM FM Utilities | 224028.78 | 224028.78 | 0 | 0 | 0
P779246 | FY07 CRDM Computing Center | 310613.68 | 310613.68 | 0 | 0 | 0
P779247 | FY07 CRDM MD Anderson library | 202169.17 | 202169.17 | 0 | 0 | 0
P779248 | FY07 CRDM Project Manangment | 66519.44 | 66519.44 | 0 | 0 | 0
P779255 | FY07 CRDM Communication Labs | 131669 | 131669 | 0 | 0 | 0
P779256 | FY07 CRDM BOR renovations | 411996.71 | 411996.71 | 0 | 0 | 0
P779258 | FY07 CRDM SR-2 Vivarium system | 14825.25 | 14825.25 | 0 | 0 | 0
P779259 | FY07 CRDM General Svs. Bldg | 751.9 | 751.9 | 0 | 0 | 0
P779357 | FY07 CRDM Hofeinz Generator | 412164.8 | 412164.8 | 0 | 0 | 0 | Norcom
P779440 | FY07 CRDM 529 SEC Shade & Elec | 20171.16 | 20171.16 | 0 | 0 | 0 | Doyle
P779444 | FY07 CRDM 551 S&R2 4th F Lab S | 3171.34 | 3171.34 | 0 | 0 | 0 | Madrigal
P779445 | FY07 CRDM 551 S&R2 3rd F Lab S | 4885.94 | 4885.94 | 0 | 0 | 0 | Madrigal
P779446 | FY07 CRDM 551 S&R2 2nd F Lab S | 3118.22 | 3118.22 | 0 | 0 | 0 | Madrigal
P779447 | FY07 CRDM 551 S&R2 1st F Lab S | 609.3 | 609.3 | 0 | 0 | 0 | Madrigal
P779448 | FY07 CRDM 532 Garrison Gym H/W | 6378 | 6378 | 0 | 0 | 0 | Madrigal
P779450 | FY07 CRDM Cameron Child Care A | 8617 | 8617 | 0 | 0 | 0 | Oliver
P779451 | FY07 CRDM E Cullen Exterior Wi | 4650 | 4650 | 0 | 0 | 0 | Javaid
P779452 | FY07 CRDM Welcome Center Exter | 3309 | 3309 | 0 | 0 | 0 | Javaid
P779453 | FY07 CRDM S&R1 & S&R2 Generato | 32717 | 28762.56 | 3645.46 | 0 | 308.98 | Gill
P779454 | FY07 CRDM E Cullen Rm 122 Reco | 1430 | 1430 | 0 | 0 | 0 | Martin
P779455 | FY07 CRDM Hilton Cont Edu Ahu2 | 14400 | 14400 | 0 | 0 | 0 | Martin
P779456 | FY07 CRDM SERC Emergency Repai | 7774.54 | 7774.54 | 0 | 0 | 0
P779457 | FY07 CRDM HSC Dock & Corridor | 20545.02 | 20545.02 | 0 | 0 | 0 | Brungardt
P779458 | FY07 CRDM HSC Hydraulic Cylind | 36381 | 36381 | 0 | 0 | 0 | Rahurkar
P779459 | FY07 CRDM S&R2 Lab 228 Water D | 8582.87 | 8582.87 | 0 | 0 | 0 | Davis
P779460 | FY07 CRDM Hilton CE Window Rep | 6452 | 6514.35 | 0 | 0 | -62.35 | Davis
P779461 | FY07 CRDM 551 S&R2 Restroom Co | 31177.24 | 20610.35 | 0 | 0 | 10566.89 | Davis
P779462 | FY07 CRDM S&R2 Hallway Abateme | 96377.61 | 95707.53 | 0 | 0 | 670.08 | Davis
P779463 | FY07 CRDM 581 Cullen Eng Roof | 5000 | 0 | 5000 | 0 | 0 | Oliver
P779464 | FY07 CRDM 586 Cameron Mold Rem | 56330.83 | 56330.83 | 0 | 0 | 0 | Oliver
P779465 | FY07 CRDM E Cullen Drain Line | 975 | 975 | 0 | 0 | 0 | Oliver
P779466 | FY07 CRDM E Cullen Fountain Me | 4535.35 | 4535.35 | 0 | 0 | 0 | Rahurkar
P779467 | FY07 CRDM GSB Domestic Water H | 5793.36 | 5793.36 | 0 | 0 | 0 | Wright
P779468 | FY07 CRDM MD Anderson Basemen | 24245.26 | 24245.26 | 0 | 0 | 0 | Jenkins
P779469 | FY07 CRDM HSCA New Condensate | 5676 | 5676 | 0 | 0 | 0 | Madrigal
P779470 | FY07 CRDM S&R2 LAB OAHU Repair | 15761.56 | 15094.13 | 0 | 0 | 667.43 | Martin
P779471 | FY07 CRDM 3rd Flr. Lobby Light | 1379.85 | 1379.85 | 0 | 0 | 0 | Rahurkar
P779472 | FY07 CRDM S&R1 Emerg Vacuum Pu | 15894.03 | 15894.03 | 0 | 0 | 0 | Madrigal
P779473 | FY07 CRDM Cullen Eng. D2 Bldg. | 87374.27 | 87374.27 | 0 | 0 | 0 | Oliver
P779474 | FY07-FY10 MD Anderson Facade | 268201.58 | 2250 | 265951.58 | 0 | 0 | Oliver
P779475 | FY07 CRDM DPS Roof & Waterproo | 14189.09 | 9227.7 | 4500 | 0 | 461.39 | Jenkins
P779476 | FY07 CRDM MD Anderson Lib Coo | 108213.44 | 83571.01 | 0 | 7678 | 16964.43 | Jenkins
P779477 | FY07 CRDM Emg plumbing repairs | 14022.53 | 12089.65 | 932.88 | 0 | 1000 | Gill
P779478 | FY07 CRDM S&R2 Gas Valves Repl | 6918.52 | 6918.52 | 0 | 0 | 0 | Wright
P779506 | FY07 CRDM S&R2 SDS Vent Stack | 2500 | 836.23 | 857.5 | 0 | 806.27 | Gill
P779507 | FY07 CRDM SERC Exterior Glass | 14491.02 | 14491.02 | 0 | 0 | 0 | Wiesman
P779508 | FY07 CRDM Cullen Eng ADA Compl | 8100 | 3853.08 | 0 | 0 | 4246.92 | Harless
P779511 | FY07 CRDM Cameron PipeCleaning | 5656 | 4635.09 | 0 | 0 | 1020.91 | Wright
P779512 | FY07 CRDM PGH Room Signs Repla | 6000 | 2097.28 | 0 | 0 | 3902.72 | Brungardt
P779514 | FY07 CRDM E Cullen VP Research | 350 | 0 | 0 | 0 | 350 | Howard
P779520 | FY07 CRDM E Cullen President's | 6684.12 | 5459.84 | 0 | 0 | 1224.28 | Davis
P779573 | FY07 GSB Sidewalk Expansion | 3010 | 2979.77 | 0 | 0 | 30.23 | Wright
P779616 | FY07 CRDM AGL and EERC voltage | 4189.66 | 0 | 0 | 0 | 4189.66 | Hardin
| Total FY07 | 6813576 | 6444449.05 | 280887.42 | 7678 | 80561.53
P779260 | FY08 CRDM CONTINGENCY | 385566.4 | 291262.14 | 0 | 0 | 94304.26
P779261 | FY08 CRDM Streets & Sidewalks | 12584.85 | 12584.85 | 0 | 0 | 0
P779261 | FY08 CRDM Streets & Sidewalks | 14140.15 | 14140.15 | 0 | 0 | 0
P779261 | FY08 CRDM Streets & Sidewalks | 85725 | 85725 | 0 | 0 | 0
P779261 | FY08 CRDM Streets & Sidewalks | 23348.77 | 23348.77 | 0 | 0 | 0
P779262 | FY08 CRDM Campus initiatives | 104500 | 104500 | 0 | 0 | 0
P779265 | FY08 CRDM Architecture Bldg | 240445.39 | 240445.39 | 0 | 0 | 0
P779266 | FY08 CRDM Campus Utilities | 345690.37 | 345690.37 | 0 | 0 | 0
P779267 | FY08 CRDM Sidewalk/Street Alt. | 45810 | 45810 | 0 | 0 | 0
P779268 | FY08 CRDM E.Cullen roof repair | 120786.13 | 120298.12 | 238.01 | 0 | 250
P779269 | FY08 CRDM Security Enhancement | 40697.64 | 40697.64 | 0 | 0 | 0
P779270 | FY08 CRDM Exterior Lighting | 43822.61 | 43822.61 | 0 | 0 | 0
P779271 | FY08 CRDM Infrastructure | 121252.25 | 121252.25 | 0 | 0 | 0
P779272 | FY08 CRDM Storm Infrastructure | 434790.01 | 434790.01 | 0 | 0 | 0
P779273 | FY08 CRDM Classroom & Corridor | 97187.64 | 96103.28 | 0 | 0 | 1084.36
P779274 | FY08 CRDM S&R-2 | 206518.75 | 206518.75 | 0 | 0 | 0
P779276 | FY08 CRDM Tunnel Upgrades | 485985 | 485985 | 0 | 0 | 0
P779277 | FY08 CRDM Master Plan | 19722.31 | 19722.31 | 0 | 0 | 0
P779278 | FY08 CRDM A. Arnold Fine Arts | 344213.45 | 344213.45 | 0 | 0 | 0
P779279 | FY08 CRDM Art Conservation | 19160.35 | 19160.35 | 0 | 0 | 0
P779280 | FY08 CRDM Landscape | 152774.22 | 152774.22 | 0 | 0 | 0
P779281 | FY08 CRDM Grounds Maintenance | 39981.1 | 39981.1 | 0 | 0 | 0
P779282 | FY08 CRDM Doors & Hardware | 26417.77 | 26417.77 | 0 | 0 | 0
P779283 | FY08 CRDM ADA Modifications | 16932.85 | 16932.85 | 0 | 0 | 0
P779284 | FY08 CRDM Fire Alarms | 98121.8 | 98121.8 | 0 | 0 | 0
P779286 | FY08 CRDM HVAC Upgrades | 307577.25 | 280464.87 | 1750 | 0 | 25362.38
P779287 | FY08 CRDM Environ.Remediation | 90013.37 | 90013.37 | 0 | 0 | 0
P779288 | FY08 CRDM Clinical Research | 16370.96 | 16370.96 | 0 | 0 | 0
P779289 | FY08 CRDM Emerg fuel tank farm | 870008.88 | 827472.84 | 41280 | 0 | 1256.04
P779290 | FY08 CRDM Bldg Envelope Repair | 148961.51 | 148961.51 | 0 | 0 | 0
P779291 | FY08 CRDM Facilities Maint. | 116972.75 | 116972.75 | 0 | 0 | 0
P779293 | FY08 CRDM Moores Sch. of Music | 11523 | 3498 | 0 | 0 | 8025
P779295 | FY08 CRDM Energy Conservation | 160194.93 | 160194.93 | 0 | 0 | 0
P779296 | FY08 CRDM NE Campus Infra | 1978360.42 | 1632885.61 | 0 | 0 | 345474.81
P779297 | FY08 CRDM Custodial Flr resurf | 19616.39 | 19616.39 | 0 | 0 | 0
P779323 | FY08 CRDM Prof dist landscape | 9325.45 | 9325.45 | 0 | 0 | 0 | Harless
P779324 | FY08 CRDM Y Bldg pre demo | 8000 | 7520 | 0 | 0 | 480 | Norcom
P779344 | FY08 CRDM 586 Cameron Elevator | 12248.51 | 12248.51 | 0 | 0 | 0
P779345 | FY08 CRDM 547 PG Hoffman roof | 4900 | 4900 | 0 | 0 | 0
P779347 | FY08 CRDM 543 Arch Rm214 Water | 24069.91 | 24069.91 | 0 | 0 | 0 | Oliver
P779348 | FY08 CRDM 503 TechLoading Dock | 17490 | 17490 | 0 | 0 | 0 | Oliver
P779350 | FY08 CRDM 543 Arch Ligh/Life S | 76186 | 76186 | 0 | 0 | 0 | Oliver
P779352 | FY08 CRDM 509 MD Anderson Ext | 164190.24 | 95250 | 41880 | 0 | 27060.24 | Oliver
P779353 | FY08 CRDM 701TMC Pharmacy Roof | 88517.69 | 87500 | 0 | 0 | 1017.69 | Oliver
P779354 | FY08 CRDM 543-509 Arch & MDA | 124749.48 | 95181.87 | 0 | 0 | 29567.61 | Oliver
P779355 | FY08 CRDM 106 TLCC Old CH8 Col | 34059 | 27598.74 | 0 | 0 | 6460.26 | Gill
P779356 | FY08 CRDM Framework Model Addi | 24440 | 23500 | 0 | 0 | 940 | LaMontagne
P779359 | FY08 CRDM 537 Law Ctr. Water I | 75018.34 | 75296.32 | 0 | 0 | -277.98 | Doyle
P779360 | FY08 CRDM 543 Architecture Bri | 201105.15 | 170574.07 | 0 | 0 | 30531.08 | Oliver
P779361 | FY08 CRDM 516 E Cullen S Entra | 73098.34 | 28712.85 | 34716.41 | 0 | 9669.08 | Oliver
P779362 | FY08 CRDM 509 MDA Barrel Gutte | 39351.84 | 39325.96 | 0 | 0 | 25.88 | Oliver
P779363 | FY08 CRDM 578 Agnes C/W Coil R | 8405 | 5807.69 | 0 | 0 | 2597.31 | Kapileshwari
P779364 | FY08 CRDM 551 S&R2 C/W Cooling | 7125 | 1923.58 | 0 | 0 | 5201.42 | Kapileshwari
P779365 | FY08 CRDM 593 HSC Pans Lab HVA | 18000 | 3187.27 | 0 | 0 | 14812.73 | Kapileshwari
P779366 | FY08 CRDM 590 Hilton Hotel Pum | 3800 | 2028.58 | 0 | 0 | 1771.42 | Kapileshwari
P779367 | FY08 CRDM 499 Fire Alarm Netwo | 3009 | 2960 | 0 | 0 | 49 | Kapileshwari
P779368 | FY08 CRDM 524 Student Svcs. As | 1895 | 1895 | 0 | 0 | 0 | Oliver
P779369 | FY08 CRDM 586 Cameron Sanitary | 40461 | 32198 | 0 | 0 | 8263 | Gill
P779370 | FY08 CRDM 544 Cemo Hall Water | 1801.38 | 1749.38 | 0 | 0 | 52 | Oliver
P779372 | FY08 CRDM 543 Arch Asbestos Sa | 513.31 | 513.31 | 0 | 0 | 0 | Wright
P779373 | FY08 CRDM 536 CPB Window Repla | 632 | 632 | 0 | 0 | 0 | Wright
P779374 | FY08 CRDM 581 Eng Fire Alarm U | 304116 | 229251.39 | 448.6 | 0 | 74416.01 | Javaid
P779375 | FY08 CRDM 585 GSB Fire Alarm U | 321148 | 126549.9 | 96800.1 | 0 | 97798 | Javaid
P779376 | FY08 CRDM 590 Hilton Pump Moni | 5737 | 4570 | 0 | 0 | 1167 | Maal
P779377 | FY08 CRDM 520 Moores Storm Dra | 4977 | 4875.41 | 0 | 0 | 101.59 | Gill
P779378 | FY08 CRDM 550 S&R1 Rm325 ACM A | 4072 | 4022.83 | 0 | 0 | 49.17 | Doyle
P779380 | FY08 CRDM 586 Cameron Human & | 9177.3 | 6840 | 0 | 0 | 2337.3 | Oliver
P779381 | FY08 CRDM 535 EHRM2 Drainage I | 43100.29 | 43100.29 | 0 | 0 | 0 | Jenkins
P779382 | FY08 CRDM Campus Wide Card Acc | 3685 | 2990.7 | 0 | 0 | 694.3 | Jenkins
P779384 | FY08 CRDM 532 Garrison Gym Car | 4744.49 | 4744.49 | 0 | 0 | 0 | Villarreal
P779385 | FY08 CRDM 585 GSB Rm177 Carpet | 5032.34 | 4661.82 | 0 | 0 | 370.52 | Villarreal
P779386 | FY08 CRDM 499 Campus Wide Spri | 21313.32 | 18884.28 | 1050 | 0 | 1379.04 | Kapileshwari
P779409 | FY08 CRDM 516 ECullen Recarpet | 768 | 768 | 0 | 0 | 0 | Jenkins
P779410 | FY08 CRDM CW Detention Bank Ma | 8500 | 8500 | 0 | 0 | 0 | LaMontagne
P779411 | FY08 CRDM 550 S&R1 Easter Week | 108000 | 88949.19 | 0 | 0 | 19050.81 | Oliver
P779412 | FY08 CRDM 544 Cemo Water Infil | 53820 | 38820 | 0 | 0 | 15000 | Miller
P779413 | FY08 CRDM 564 Fleming Dom Wate | 1232.42 | 1232.42 | 0 | 0 | 0 | Wright
P779414 | FY08 CRDM 585 GSB Paint Booth | 65918.73 | 65918.73 | 0 | 0 | 0 | Oliver
P779415 | FY08 CRDM 505 Animal Wash Plum | 4221 | 1716.76 | 0 | 1037.5 | 1466.74 | Javaid
P779416 | FY08 CRDM 516 Cullen Emerg Wat | 20737.5 | 16830.57 | 0 | 0 | 3906.93 | Oliver
P779417 | FY08 CRDM 589 Fine Arts Orgal | 24651.9 | 24651.9 | 0 | 0 | 0 | Doyle
P779418 | FY08 CRDM 586 Cameron Sewage L | 1917 | 1915 | 0 | 0 | 2 | Oliver
P779419 | FY08 CRDM 520 Moores Music Str | 28915.36 | 16544 | 9592 | 0 | 2779.36 | Lawrence
P779420 | FY08 CRDM 590 Hilton E&G Study | 6669.21 | 6669.21 | 0 | 0 | 0 | Lawrence
P779421 | FY08 CRDM CW Facility Conditio | 325369 | 41121.01 | 284247.99 | 0 | 0 | Norcom
P779423 | FY08 CRDM 578 Agnes Hall Cooli | 3500 | 2652.64 | 0 | 0 | 847.36 | Kapileshwari
P779424 | FY08 CRDM 501 Roy Cullen Trans | 19825 | 19825 | 0 | 0 | 0 | Kapileshwari
P779425 | FY08 CRDM 509 MDA Library Emer | 3564.74 | 3564.74 | 0 | 0 | 0 | Wright
P779426 | FY08 CRDM 534 Heyne Transfer S | 14860 | 14860 | 0 | 0 | 0 | Kapileshwari
P779427 | FY08 CRDM 551 S&R2 Water Drain | 5000 | 1771.76 | 0 | 0 | 3228.24 | Schneller
P779428 | FY08 CRDM 509 MDA Library Hand | 56691.8 | 41080 | 0 | 0 | 15611.8 | Jenkins
P779429 | FY08 CRDM 579 Engineering 2nd | 5185.21 | 5185.21 | 0 | 0 | 0 | Kapileshwari
P779430 | FY08 CRDM 579 Engineering 3rd | 5185.21 | 5185.21 | 0 | 0 | 0 | Kapileshwari
P779431 | FY08 CRDM 550 S&R1 Protective | 64250 | 64193.7 | 0 | 0 | 56.3 | Doyle
P779435 | FY08 CRDM 529 SEC Emergency Li | 3703 | 3224.12 | 0 | 0 | 478.88 | Doyle
P779485 | FY08 CRDM E.Cullen Water Line | 9012.5 | 8750 | 0 | 0 | 262.5 | Gill
P779487 | FY08 CRDM Cont Ed ADA Upgrades | 3678.13 | 3420 | 0 | 0 | 258.13 | Jenkins
P779488 | FY08 CRDM SER Classrooom HVAC | 21867.76 | 21330.47 | 718.75 | 0 | -181.46 | Martin
P779489 | FY08 CRDM E Cullen Elevator En | 3106.4 | 1757.41 | 0 | 0 | 1348.99 | Davis
P779490 | FY08 CRDM Parking Lot 19 E Inf | 8315 | 8315 | 0 | 0 | 0 | Gill
P779491 | FY08 CRDM Cullen Eng. Lab E411 | 10320 | 9990 | 0 | 0 | 330 | Oliver
P779492 | FY08 CRDM S&R 1 Sewer Ejector | 18353.93 | 18353.93 | 0 | 0 | 0 | Wright
P779493 | FY08 CRDM MOP Restroom Trailer | 2280 | 2280 | 0 | 0 | 0 | Davis
P779494 | FY08 CRDM MelcherHall Handrail | 1210.25 | 1175.5 | 0 | 0 | 34.75 | Jenkins
P779495 | FY08 CRDM MDA Library Basement | 7210 | 5138.77 | 0 | 0 | 2071.23 | Gill
P779496 | FY08 CRDM Arch. Indoor Air Qua | 21958.5 | 16150 | 0 | 0 | 5808.5 | Oliver
P779497 | FY08 CRDM Arch 4th F Air Balan | 12460 | 12260 | 0 | 0 | 200 | Martin
P779498 | FY08 CRDM Welcome Ctr Odor Inv | 3240 | 2397.07 | 680 | 0 | 162.93 | Gill
P779499 | FY08 CRDM E. Cullen TDLR Upgra | 8352 | 8352 | 0 | 0 | 0 | Wiesman
P779500 | FY08 CRDM Wortham Thtr Cleanin | 881.8 | 881.8 | 0 | 0 | 0 | Norcom
| Total FY08 | 10000000 | 8620546.13 | 513401.86 | 1037.5 | 865014.51
P779300 | FY09 CRDM Contingency | 415417.8 | 291262.14 | 0 | 0 | 124155.66 | Rockwell
P779301 | FY09 CRDM Streets & Sidewalks | 5705.95 | 5705.95 | 0 | 0 | 0 | Villarreal
P779301 | FY09 CRDM Streets & Sidewalks | 16113.75 | 16113.75 | 0 | 0 | 0 | Villarreal
P779301 | FY09 CRDM Streets & Sidewalks | 140169.27 | 140169.27 | 0 | 0 | 0 | Villarreal
P779302 | FY09 CRDM Classrooms & Corrido | 406580.03 | 406580.03 | 0 | 0 | 0 | Norcom
P779304 | FY09 CRDM Moore's slab repair | 3000 | 2500 | 0 | 0 | 500 | Norcom
P779305 | FY09 CRDM Campus AHU Sys. | 27639.07 | 27639.07 | 0 | 0 | 0 | Norcom
P779306 | FY09 CRDM Bldg Envelope Repair | 63804.66 | 63804.66 | 0 | 0 | 0 | Norcom
P779307 | FY09 CRDM Environmental Remedi | 23298.08 | 23298.08 | 0 | 0 | 0 | Norcom
P779309 | FY09 CRDM Sanitary & Storm Inf | 35605.2 | 33903.2 | 1702 | 0 | 0 | Norcom
P779310 | FY09 CRDM Sec Cameras/Lighting | 560.7 | 560.7 | 0 | 0 | 0 | Norcom
P779314 | FY09 CRDM ADA Corrections | 18773.06 | 18773.06 | 0 | 0 | 0 | Norcom
P779316 | FY09 CRDM Door & Hardware | 93800.12 | 93800.12 | 0 | 0 | 0 | Norcom
P779317 | FY09 CRDM Art Conservation | 804.09 | 804.09 | 0 | 0 | 0 | Norcom
P779318 | FY09 CRDM Exterior Card Access | 92750 | 92813.53 | 0 | 0 | -63.53 | Norcom
P779319 | FY09 CRDM Bldg Deferred Mntce. | 147397.54 | 147397.54 | 0 | 0 | 0 | Norcom
P779322 | FY09 CRDM Landscape NE Precin | 9833.06 | 9833.06 | 0 | 0 | 0 | Norcom
P779346 | FY09 CRDM 587Farish Hall Class | 4748.75 | 3412.81 | 0 | 0 | 1335.94 | Barnes Jr
P779349 | FY09 CRDM 543 Arch Mold Remed | 93979.29 | 93979.29 | 0 | 0 | 0 | Oliver
P779351 | FY09 CRDM Arch Water Proof | 132529.87 | 132529.87 | 0 | 0 | 0 | Oliver
P779383 | FY09 CRDM 543 Arch. Fire Alarm | 274196 | 258244.45 | 431.6 | 0 | 15519.95 | Kapileshwari
P779387 | FY09 CRDM 501 CWBasic Access C | 101553.26 | 82376.45 | 11821.15 | 0 | 7355.66 | Jenkins
P779388 | FY09 CRDM 551 S&R2 Trench Drai | 3054.24 | 1529.04 | 0 | 0 | 1525.2 | Barnes
P779389 | FY09 CRDM 499 Lynn Eusan Park | 28836 | 24700 | 0 | 0 | 4136 | Gill
P779390 | FY09 CRDM 524 SS Bldg. Fire Al | 113344 | 6790 | 69372.61 | 0 | 37181.39 | Doyle
P779391 | FY09 CRDM 499 CW Fire Alarm Ne | 62092 | 61185.09 | 0 | 0 | 906.91 | Kapileshwari
P779392 | FY09 CRDM CW Utility Infrastru | 145950 | 97509.84 | 0 | 0 | 48440.16 | Kapileshwari
P779394 | FY09 CRDM 549 SW Rm102 Light M | 13723.77 | 13723.77 | 0 | 0 | 0 | Javaid
P779396 | FY09 CRDM 506 Comm Air Handler | 301641 | 286768.35 | 0 | 0 | 14872.65 | Ruck
P779397 | FY09 CRDM 530 RS Fire Hydrant | 7485 | 7485 | 0 | 0 | 0 | Oliver
P779398 | FY09 CRDM 516 ECullen Restroom | 400 | 161.19 | 0 | 0 | 238.81 | Howard
P779399 | FY09 CRDM 516 Cullen Arch&Eng | 51346 | 49856.39 | 0 | 0 | 1489.61 | Norcom
P779400 | FY09 CRDM 516 Cullen Air Path | 7360 | 6817.21 | 0 | 0 | 542.79 | Kapileshwari
P779401 | FY09 CRDM 516 E Cullen Rm 125 | 2518.52 | 2518.52 | 0 | 0 | 0 | Norcom
P779402 | FY09 CRDM 509 MD Anderson Engi | 70450.5 | 67000 | 0 | 0 | 3450.5 | Jenkins
P779403 | FY09 CRDM 528 Melcher Hall Rec | 1773 | 1773 | 0 | 0 | 0 | Wright
P779404 | FY09 CRDM 505 Opt Termite Trea | 15342.74 | 15342.74 | 0 | 0 | 0 | Wright
P779405 | FY09 CRDM 525 Hlth Ctr Transfe | 1680 | 1680 | 0 | 0 | 0 | Kapileshwari
P779406 | FY09 CRDM 505 Opt Transfer Con | 2367 | 2367 | 0 | 0 | 0 | Kapileshwari
P779408 | FY09 CRDM 515 Power Plant Manh | 1720 | 1720 | 0 | 0 | 0 | Kapileshwari
P779433 | FY09 CRDM 501 Roy Cullen HVAC | 3675 | 3500 | 0 | 0 | 175 | Oliver
P779434 | FY09 CRDM 520 Moores Handrail | 20994.05 | 19085.55 | 0 | 0 | 1908.5 | Jenkins
P779437 | FY09 CRDM 528 Melcher Hall C/W | 8000 | 5333.59 | 0 | 0 | 2666.41 | Kapileshwari
P779438 | FY09 CRDM 543 Architecture AHU | 3181.22 | 3061.56 | 0 | 0 | 119.66 | Kapileshwari
P779439 | FY09 CRDM 551 S&R2 Lab 329 HVA | 7120 | 6260.2 | 0 | 0 | 859.8 | Kapileshwari
P779441 | FY09 CRDM CW Utility Infrastru | 51500 | 44560.54 | 4900 | 0 | 2039.46 | Kapileshwari
P779442 | FY09 CRDM Central Utility Plan | 4785 | 4025 | 0 | 0 | 760 | Gill
P779443 | FY09 CRDM 516 E Cullen 1st F A | 22426.46 | 22426.46 | 0 | 0 | 0 | Davis
P779449 | FY09 CRDM OB Woods Irrigation | 10924.95 | 9525 | 0 | 0 | 1399.95 | Smith
P779505 | FY09 CRDM Fleming Bldg. Valve | 15550 | 12537.1 | 0 | 0 | 3012.9 | Ivy
P779521 | FY09 CRDM Plant Chiller 2A Mot | 75000 | 21450.02 | 4302.48 | 2514.95 | 46732.55 | Kapileshwari
P779523 | FY09 CRDM Fire Extinguisher Re | 11350 | 9550 | 0 | 0 | 1800 | Norcom
P779526 | FY09 CRDM Fleming Rm. 60 Domes | 2767 | 2764.2 | 0 | 0 | 2.8 | Wright
P779530 | FY09 CRDM Cullen Eng Asbestos | 383 | 383 | 0 | 0 | 0 | Wiesman
P779556 | FY09 CRDM UH Campus Room Signs | 18000 | 2543.12 | 0 | 0 | 15456.88 | Wanjagi
P779474 | FY07-FY10 MD Anderson Facade | 200000 | 193382.56 | 6617.44 | 0 | 0 | Oliver
| Total FY09 | 3395000 | 2954816.16 | 99147.28 | 2514.95 | 338521.61
P779325 | FY10 CRDM Contingency | 291262.14 | 291262.14 | 0 | 0 | 0 | Norcom
P779327 | FY10 CRDM Painting & Carpet | 14645.04 | 14645.04 | 0 | 0 | 0 | Villarreal
P779329 | FY10 CRDM Environmental Issues | 3345.38 | 3345.38 | 0 | 0 | 0 | Norcom
P779334 | FY10 CRDM ADA Corrections | 4228.02 | 4228.02 | 0 | 0 | 0 | McKinney
P779422 | FY10 CRDM FPC Master Specifica | 225000 | 173678.3 | 26219.5 | 22.5 | 25079.7 | Yancey
P779436 | FY10 CRDM 564 Fleming Classroo | 423881 | 283740.26 | 2916 | 0 | 137224.74 | Javaid
P779474 | FY07-FY10 MD Anderson Facade | 842638.42 | 430255 | 152865.73 | 0 | 259517.69 | Oliver
| Total FY10 | 1805000 | 1201154.14 | 182001.23 | 22.5 | 421822.13
P779480 | FY11 CRDM Contingency | 421942.4 | 79.33 | 0 | 0 | 421863.07 | Rockwell
P779486 | FY11 CRDM Main Campus Utility | 345340 | 308816.98 | 31951.7 | 0 | 4571.32 | Ivy
P779501 | FY11 CRDM Architectue Vestibul | 13390 | 390 | 0 | 0 | 13000 | Oliver
P779502 | FY11 CRDM Student Svc Bldg Sky | 3509.32 | 3202.21 | 0 | 0 | 307.11 | Jenkins
P779503 | FY11 CRDM Melcher & Garrison G | 52363.46 | 33467.58 | 2583 | 0 | 16312.88 | Wiesman
P779504 | FY11 CRDM CW Obsolete Honeywel | 14789.73 | 14789.73 | 0 | 0 | 0 | Martin
P779509 | FY11 CRDM MD Anderson Lib Carp | 28590.34 | 26435.85 | 0 | 0 | 2154.49 | Jenkins
P779510 | FY11 CRDM MDA Lib Ext Assessme | 54105.9 | 46593.6 | 4406.4 | 0 | 3105.9 | Oliver
P779513 | FY11 CRDM Social Work Fire Pum | 24837.4 | 1332.21 | 21980 | 0 | 1525.19 | Kapileshwari
P779515 | FY11 CRDM CW Water Sanitary St | 170000 | 17703.46 | 146648 | 0 | 5648.54 | Ivy
P779516 | FY11 CRDM CW Transportation Ma | 140000 | 22141.58 | 114940 | 0 | 2918.42 | Ivy
P779517 | FY11 CRDM Y Bldg. Stduy&Design | 206485.39 | 73066.59 | 47816 | 0 | 85602.8 | Norcom
P779518 | FY11 CRDM CW Ruptured Coil Rep | 356895 | 0 | 0 | 0 | 356895 | Oliver
P779519 | FY11 CRDM SR1 & SR2 Generator | 246990.29 | 0 | 0 | 0 | 246990.29 | Gill
P779522 | FY11 CRDM CCOE-S40 Flooring Re | 11899.33 | 8659.93 | 0 | 0 | 3239.4 | Davis
P779524 | FY11 CRDM Cullen Eng Fire Supp | 379065.75 | 13040.75 | 3000 | 0 | 363025 | Oliver
P779525 | FY11 CRDM Optometry Ext Facade | 42070.35 | 14945.35 | 25230 | 0 | 1895 | Norcom
P779527 | FY11 CRDM Power Plant Chiller | 162845.45 | 152633.07 | 0 | 0 | 10212.38 | Gill
P779528 | FY11 CRDM Wortham Theater Door | 28750.7 | 1028.84 | 27393.89 | 0 | 327.97 | Brungardt
P779529 | FY11 CRDM Arch Mold Remediatio | 6407.12 | 3986.62 | 865 | 0 | 1555.5 | Oliver
P779531 | FY11 CRDM FCA Phase 1 and 2 | 95176.33 | 41120.99 | 42305.01 | 0 | 11750.33 | Norcom
P779532 | FY11 CRDM Campus Grounds Fire | 9717.28 | 8628.23 | 0 | 0 | 1089.05 | Oliver
P779533 | FY11 CRDM Roy Cullen Exterior | 56650 | 17577.83 | 6800 | 0 | 32272.17 | Connell
P779534 | FY11 CRDM UH Generator & ATS R | 49965 | 38087.29 | 2000 | 0 | 9877.71 | Gill
P779535 | FY11 CRDM SERC Transite Pipe R | 7671.51 | 7672.38 | 0 | 0 | -0.87 | Ivy
P779536 | FY11 CRDM S&R2 Animal Care Ope | 112315.32 | 3271.32 | 106936.5 | 2107.5 | 0 | Oliver
P779537 | FY11 CRDM Law Residence Hall S | 10235.76 | 10235.76 | 0 | 0 | 0 | Gill
P779538 | FY11 CRDM GSB/Cameron Hot Wate | 27604 | 25365.08 | 0 | 0 | 2238.92 | Gill
P779539 | FY11 CRDM E Cullen Flood Break | 11541.12 | 11541.12 | 0 | 0 | 0 | Gill
P779540 | FY11 CRDM S&R1 Window Replacem | 3211 | 2881.04 | 0 | 0 | 329.96 | Wright
P779541 | FY11 CRDM E Cullen Rms. 6 & 8 | 1431 | 1169.14 | 0 | 0 | 261.86 | Wright
P779542 | FY11 CRDM E Cullen Install ADA | 4074.5 | 3482.01 | 0 | 0 | 592.49 | Wright
P779543 | FY11 CRDM Hilton Window Replac | 1873 | 1631.31 | 0 | 0 | 241.69 | Wright
P779544 | FY11 CRDM HSC Window Replaceme | 1928.2 | 1722.48 | 0 | 0 | 205.72 | Wright
P779545 | FY11 CRDM Hilton (E&G) Control | 302511 | 8811 | 0 | 0 | 293700 | Rahurkar
P779546 | FY11 CRDM Health Center Room 1 | 654 | 550.36 | 0 | 0 | 103.64 | Wright
P779547 | FY11 CRDM Cameron Smoke Test S | 46448 | 40459.68 | 0 | 0 | 5988.32 | Gill
P779548 | FY11 CRDM S&R1 Breaker Repair | 74160 | 30157.11 | 8500 | 0 | 35502.89 | Rahurkar
P779549 | FY11 CRDM Cullen Eng Carrier R | 32529.17 | 24630.27 | 0 | 0 | 7898.9 | Oliver
P779550 | FY11 CRDM Entrance 14 Curb Mod | 19071.79 | 17412.01 | 0 | 0 | 1659.78 | Ivy
P779551 | FY11 CRDM Fleming Domestic Hot | 4148 | 3569.33 | 0 | 0 | 578.67 | Wright
P779552 | FY11 CRDM Exterior Concrete St | 38812.67 | 37349.97 | 854 | 0 | 608.7 | Connell
P779553 | FY11 CRDM Cullen Eng. Chill Wa | 20682.83 | 17276.05 | 0 | 20437.66 | 3651.95 | Wiesman
P779554 | FY11 CRDM Campus Wide Fire Ext | 14986.5 | 10261.5 | 1925 | 0 | 2800 | Oliver
P779555 | FY11 CRDM Optometry Elv. Jack | 46453 | 29525 | 0 | 0 | 16928 | Rahurkar
P779557 | FY11 CRDM Water Leak Outside C | 23638.7 | 21261.76 | 0 | 0 | 2376.94 | Gill
P779558 | FY11 CRDM E. Cullen Basement F | 40640.31 | 19197.1 | 18443.21 | 0 | 3000 | Jenkins
P779559 | FY11 CRDM S&R2 Animal Care San | 21686.55 | 19341.54 | 0 | 0 | 2345.01 | Gill
P779560 | FY11 CRDM Arch Visible Mold Re | 107789.98 | 92258.59 | 0 | 0 | 15531.39 | Oliver
P779562 | FY11 CRDM S&E Annex AGL Domest | 52957.92 | 44633.58 | 0 | 0 | 8324.34 | Gill
P779563 | FY11 CRDM HSC Rm. 143A Mold Re | 9011.05 | 8594.46 | 0 | 0 | 416.59 | Jenkins
P779564 | FY11 CRDM GSB 1st Floor Restro | 13518.75 | 393.75 | 12500 | 0 | 625 | Jenkins
P779565 | FY11 CRDM Cameron Grease Trap | 5847.84 | 170.33 | 4954.84 | 0 | 722.67 | Gill
P779566 | FY11 CRDM Central Plant Chille | 124452.31 | 51910.82 | 66594 | 0 | 5947.49 | Gill
P779567 | FY11 CRDM Hilton/Moody Water L | 161695 | 20203.01 | 111900.86 | 0 | 29591.13 | Gill
P779568 | FY11 CRDM Trailer Village Util | 5665 | 2557.25 | 0 | 0 | 3107.75 | Ivy
P779569 | FY11 CRDM Cullen Domestic Boos | 13143 | 8302.16 | 0 | 0 | 4840.84 | Gill
P779570 | FY11 CRDM Eng. Northside Domes | 2603.94 | 2374.78 | 0 | 0 | 229.16 | Gill
P779571 | FY11 CRDM Wortham Theatre Awni | 1030 | 414.14 | 0 | 0 | 615.86 | Ivy
P779572 | FY11 CRDM AgnesHall Rms Refres | 176505.94 | 0 | 148626.4 | 0 | 27879.54 | Connell
P779574 | FY11 CRDM SPA Awning N. Side | 17878.74 | 0 | 15850 | 0 | 2028.74 | Ivy
P779575 | FY11 CRDM Melcher Hall Exterio | 53154.36 | 143.57 | 49148.75 | 0 | 3862.04 | Jenkins
P779577 | FY11 CRDM Cameron Vent Piping | 26944 | 19669.76 | 0 | 0 | 7274.24 | Gill
P779578 | FY11 CRDM Water Main Leak West | 20630 | 17755 | 0 | 0 | 2875 | Gill
P779579 | FY11 CRDM MDA Library Ductile | 2664 | 2487 | 0 | 0 | 177 | Gill
P779580 | FY11 CRDM Parking Lot 19-D Eig | 3326 | 3230 | 0 | 0 | 96 | Gill
P779581 | FY11 CRDM Krost Hall Six-Inch | 3138.63 | 2947.63 | 0 | 0 | 191 | Gill
P779582 | FY11 CRDM SEC Shade Protection | 53652.09 | 0 | 47354.01 | 0 | 6298.08 | Connell
P779583 | FY11 CRDM Cullen Eng. ADA/TAS | 30790.03 | 0 | 26464 | 0 | 4326.03 | Oliver
P779584 | FY11 CRDM Eight-Inch Water Mai | 8461 | 7808 | 0 | 0 | 653 | Gill
P779585 | FY11 CRDM S&R2 #141D Ongoing T | 5799.07 | 3520 | 1253.82 | 0 | 1025.25 | Norcom
P779586 | FY11 CRDM Architecture Indoor | 45633 | 0 | 36000 | 0 | 9633 | Oliver
P779587 | FY11 CRDM Architecture Sprinkl | 6577.52 | 5905.21 | 0 | 0 | 672.31 | Oliver
P779588 | FY11 CRDM Cullen Eng. Mech. Rm | 25970 | 0 | 18000 | 0 | 7970 | Oliver
P779589 | FY11 CRDM SW Damaged Carpet/Re | 9516.15 | 8550 | 0 | 0 | 966.15 | Jenkins
P779590 | FY11 CRDM Tech ADA Automatic D | 3975 | 0 | 3750 | 0 | 225 | Jenkins
P779591 | FY11 CRDM SPA East Awning Repl | 46932.49 | 0 | 40634 | 0 | 6298.49 | Ivy
P779592 | FY11 CRDM SR2 Animal Care Sani | 7220 | 0 | 4875 | 0 | 2345 | Gill
P779593 | FY11 CRDM CW Four-inch Irrigat | 5120.59 | 0 | 4655.59 | 0 | 465 | Gill
P779594 | FY11 CRDM AA Auditorium Water | 15308.85 | 0 | 14578.85 | 0 | 730 | Gill
P779595 | FY11 CRDM CW Six-inch Water Ma | 3676.65 | 0 | 3501.65 | 0 | 175 | Gill
P779596 | FY11 CRDM Water Leak by Parkin | 3406.25 | 0 | 3244.25 | 0 | 162 | Gill
P779597 | FY11 CRDM Eng. EERC Front Wate | 3885.86 | 0 | 3700.86 | 0 | 185 | Gill
P779598 | FY11 CRDM McElhinney Hall New | 11968 | 148.08 | 10017 | 0 | 1802.92 | Gill
P779599 | FY11 CRDM SR2 AHU#4-D Water Co | 6790.3 | 0 | 0 | 0 | 6790.3 | Rahurkar
P779600 | FY11 CRDM Arch Rm. 206 Water D | 27421.85 | 0 | 21689.06 | 0 | 5732.79 | Simmons
P779601 | FY11 CRDM SERC 1st F. Northsid | 3190 | 0 | 0 | 0 | 3190 | Wright
P779602 | FY11 CRDM KUHT 1st F. Front En | 1894 | 114.52 | 0 | 0 | 1779.48 | Wright
P779603 | FY11 CRDM South Park Exterior | 11996.32 | 0 | 0 | 0 | 11996.32 | Wright
P779604 | FY11 CRDM McElhinney Damaged C | 2980 | 0 | 0 | 0 | 2980 | Wright
P779605 | FY11 CRDM Social Work Carpet F | 1511.13 | 0 | 1296 | 0 | 215.13 | Jenkins
P779606 | FY11 CRDM Fine Arts NE Side Wa | 12342.2 | 0 | 0 | 0 | 12342.2 | Gill
P779607 | FY11 CRDM Heyne Bldg. Northsid | 2858 | 0 | 0 | 0 | 2858 | Gill
P779608 | FY11 CRDM Biology Greenhouse E | 4663 | 0 | 0 | 0 | 4663 | Gill
P779609 | FY11 CRDM Heyne Bldg. Southsid | 3702 | 0 | 0 | 0 | 3702 | Gill
P779610 | FY11 CRDM Tech 1 Annex Southsi | 11455.2 | 0 | 0 | 0 | 11455.2 | Gill
P779611 | FY11 CRDM Tech 1 Eastside Wate | 11398 | 0 | 0 | 0 | 11398 | Gill
P779612 | FY11 CRDM PGH Northside Three | 14665.53 | 0 | 0 | 0 | 14665.53 | Gill
P779613 | FY11 CRDM PGH Southside Water | 4061.52 | 0 | 0 | 0 | 4061.52 | Gill
P779614 | FY11 CRDM Law Hall Southside W | 6161.52 | 0 | 0 | 0 | 6161.52 | Gill
P779615 | FY11 CRDM MDA Library Northsid | 5639.23 | 0 | 0 | 0 | 5639.23 | Gill
P779617 | FY11 CRDM Calhoun Lofts Eastsi | 1250.27 | 0 | 0 | 0 | 1250.27 | Gill
|  | 5013923.55 | 1500593.98 | 1265166.65 | 22545.16 | 2246300.59
P779576 | FY12 CRDM Contingency | 8396893 | 0 | 0 | 0 | 8396893 | Rockwell
| Total FY12 | 8396893 | 0 | 0 | 0 | 8396893
Total Available Funds | [5 empty] | 9071429.68
Reserved Emergency Funding (25% of available funds) | [5 empty] | 2267857.42
Total Dollars Available for Allocation | [5 empty] | 6803572.26
P779321 | FY09 CRDM Cooling Tower 5 | 6605000 | 5128727.28 | 1476272.72 | 0 | 0 | Norcom
P779342 | FY10 CRDM Cooling Tower 4 Repl | 2970000 | 2885688.63 | 84311.37 | 0 | 0 | Kapileshwari
P779343 | FY10 CRDM Central Plant Expans | 5225000 | 1846527.21 | 3378502.79 | 0 | -30 | Kapileshwari
P779481 | FY11 CRDM Central Plant Expans | 4996670 | 4996237.64 | 0 | 0 | 432.36 | Buehler
P779482 | FY12 CRDM Central Plant Expans | 5903107 | 5507621.19 | 398120.17 | 0 | -2634.36 | Buehler
P779483 | FY13 CRDM Central Plant Expans | 7325297 | 1483130.94 | 4948046.06 | 0 | 894120 | Buehler
P779484 | FY14 CRDM Central Plant Expans | 5378122 | 78222.44 | 1174275.46 | 0 | 4125624.1 | Buehler
| Total CUP | 38403196 | 21926155.33 | 11459528.57 | 0 | 5017512.1
Projected CRDM Allocations
FY12 | FY12 CRDM |  | 14300000
| FY12 Central Plant Allocation |  | 5903107
| Emergency Contingency Reserve |  | 2099223.25
| Remaining Balance |  | 6297669.75
FY13 | FY13 CRDM |  | 10000000
| FY13 CRDM Central Plant Expans |  | 7325297
| Emergency Contingency Reserve |  | 668675.75
| Projected Balance |  | 2006027.25
FY14 | FY14 CRDM |  | 10000000
| FY14 CRDM Central Plant Expans |  | 5378122
| Emergency Contingency Reserve |  | 1155469.5
| Projected Balance |  | 3466408.5